## Sheet1
PROJECT PROCESS GROUP | KNOWLRDGE AREA | S.N | PROCESS | INPUTS | TOOLS & TECHNIQUE | OUTPUTS
INITIATING | INTEGRATION | 1 | Develop Project Charter | Project statement of work | Expert Judgment | Project Charter | intitiating
|  |  |  | Business case | Facilitated technique |  | intitiating
|  |  |  | agreements |  |  | intitiating
|  |  |  | Enterprise Environmental Factors |  |  | intitiating
|  |  |  | Organization Process assets |  |  | intitiating
| project STAKEHOLDER MANG. | 2 | Identify Stakeholders | Project Charter | Stakeholder Analysis | Stakeholder Register | intitiating
|  |  |  | Procurement Documents | Expert Judgment |  | intitiating
|  |  |  | Enterprise Environmental Factors | meeting |  | intitiating
|  |  |  | Organization Process assets |  |  | intitiating
PLANNING | INTEGRATION | 3 | Develop Project Management Plan | Project Charter | Expert Judgment | Project Management Plan | planning
|  |  |  | Outputs From Planning Processes |  |  | planning
|  |  |  | Enterprise Environmental Factors | Facilitated technique |  | planning
|  |  |  | Organization Process assets |  |  | planning
| scope | 4 | plan scope management | project management plan | Expert Judgment | scope management plan | planning
|  |  |  | project charter |  |  | planning
|  |  |  | Enterprise Environmental Factors | meeting | requirements management plan | planning
|  |  |  | Organization Process assets |  |  | planning
| scope | 5 | Collect Requirements | scope management plan | Interviews | Requirement Documentation | planning
|  |  |  | requirements management plan | Focus Groups | Requirements Traceability Matrix | planning
|  |  |  | stakeholder management plan | Facilitated Workshops |  | planning
|  |  |  | Project Charter | Group Creativity Techniques |  | planning
|  |  |  | Stakeholder Register | Group Decision Making Techniques |  | planning
[5 empty] | Questionnaires and Surveys |  | planning
[5 empty] | Observations |  | planning
[5 empty] | Prototypes |  | planning
[5 empty] | Benchmarking |  | planning
[5 empty] | context diagrams |  | planning
[5 empty] | document analysis |  | planning
| scope | 6 | Define Scope | scope management plan | Expert Judgment | Project Scope Statement | planning
|  |  |  | Project Charter | Product analysis | Project Document Updates | planning
|  |  |  | Requirement Documentation | Alternatives generation |  | planning
|  |  |  | Organization Process assets | Facilitated Workshops |  | planning
| scope | 7 | Create WBS | scope management plan | Decomposition | Scope Baseline | planning
|  |  |  | Project Scope Statement |  |  | planning
|  |  |  | Requirement Documentation | Expert Judgment | Project Document Updates | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 8 | plan schedule management | project management plan | Expert Judgment | schedule management plan | planning
|  |  |  | Project Charter | analytical techniques |  | planning
|  |  |  | Enterprise Environmental Factors | meeting |  | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 9 | Define Activities | schedule management plan | Decomposition | Activity List | planning
|  |  |  | Scope Baseline | Rolling Wave Planning | Activity Attributes | planning
|  |  |  | Enterprise Environmental Factors | Expert Judgment | Milestone List | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 10 | Sequence Activities | schedule management plan | Precedence Diagramming Method (PDM) | Project Schedule Network Diagram | planning
|  |  |  | Activity List | Dependency Determination | Project Document Updates | planning
|  |  |  | Activity Attributes | leads and lag |  | planning
|  |  |  | Milestone List |  |  | planning
|  |  |  | Project Scope Statement |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 11 | Estimate Activity Resources | schedule management plan | Expert Judgment | Activity Resource Requirements | planning
|  |  |  | Activity List | Alternatives Analysis | Resource Breakdown Structure | planning
|  |  |  | Activity Attributes | Published Estimating Data | Project Document Updates | planning
|  |  |  | Resource Calendars | Bottom-Up Estimating |  | planning
|  |  |  | Risk Register | Project Management Software |  | planning
|  |  |  | Activity cost Estimate |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 12 | Estimate Activity Duration | schedule management plan | Expert Judgment | Activity Duration Estimate | planning
|  |  |  | Activity List | Analogous Estimating | Project Document Updates | planning
|  |  |  | Activity Attributes | Parametric Estimating |  | planning
|  |  |  | Activity Resource Requirements | Three-Point Estimates |  | planning
|  |  |  | Resource Calendars | Group Decision Making Techniques |  | planning
|  |  |  | Project Scope Statement | Reserve Analysis |  | planning
|  |  |  | Risk Register |  |  | planning
|  |  |  | resouece breakdown structure |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| TIME | 13 | Develop Schedule | schedule management plan | Schedule Network Analysis | Schedule Baseline | planning
|  |  |  | Activity List | Critical Path Method | Project Schedule | planning
|  |  |  | Activity Attributes | Critical Chain Method | Schedule data | planning
|  |  |  | Project Schedule Network Diagram | Resource optimization techniques | Schedule Data | planning
|  |  |  | Activity Resource Requirements | modeling techniques | project calendars | planning
|  |  |  | Resource Calendars | Leads and Lags | Project Management Plan Update | planning
|  |  |  | Activity Duration Estimate | Schedule Compression | Project Document Updates | planning
|  |  |  | Project Scope Statement | Scheduling Tool |  | planning
|  |  |  | Risk Register |  |  | planning
|  |  |  | Project Staff assignment |  |  | planning
|  |  |  | resouece breakdown structure |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| cost | 14 | plan cost management | Project Management Plan | Expert Judgment | cost management plan | planning
|  |  |  | Project Charter | analytical techniques |  | planning
|  |  |  | Enterprise Environmental Factors | meeting |  | planning
|  |  |  | Organization Process assets |  |  | planning
| COST | 15 | Estimate Costs | cost management plan | Expert Judgment | Activity Cost Estimate | planning
|  |  |  | Human Resource management Plan | Analogous Estimating | Basis Of Estimate | planning
|  |  |  | Scope Baseline | Parametric Estimating | Project Document Updates | planning
|  |  |  | Project Schedule | Bottom-Up Estimating |  | planning
|  |  |  | Risk Register | Three-Point Estimates |  | planning
|  |  |  | Enterprise Environmental Factors | Reserve Analysis |  | planning
|  |  |  | Organization Process assets | Cost of Quality |  | planning
[5 empty] | Project Management Software |  | planning
[5 empty] | Vendor Bid Analysis |  | planning
[5 empty] | Group Decision Making Techniques |  | planning
| COST | 16 | Determine Budget | cost management plan | Cost Aggregation | Cost Baseline | planning
|  |  |  | Scope Baseline | Reserve Analysis | Project Funding Requirements | planning
|  |  |  | Activity Cost Estimate | Expert Judgment | Project Document Updates | planning
|  |  |  | Basis Of Estimate | Historical Relationships |  | planning
|  |  |  | Project Schedule | Funding Limit Reconciliation |  | planning
|  |  |  | Resource Calendars |  |  | planning
|  |  |  | Risk Register |  |  | planning
|  |  |  | agreements |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| QUALITY | 17 | Plan Quality management | Project Management Plan | Cost-Benefit Analysis | Quality Management Plan | planning
|  |  |  | Stakeholder Register | Cost of Quality | Process Improvement Plan | planning
|  |  |  | Risk Register | Seven basic quality tools | Quality Metrics | planning
|  |  |  | requirements documentation | Benchmarking | Quality Checklists | planning
|  |  |  | Enterprise Environmental Factors | Design of Experiments | Project Document Updates | planning
|  |  |  | Organization Process assets | Statical Sampling |  | planning
[5 empty] | Additional Quality Planning Tools |  | planning
[5 empty] | meeting |  | planning
| HUMAN RESOURCE | 18 | plan human resoursce management | Project Management Plan | Organization Chart and Position Descriptions | Human Resource Plan | planning
|  |  |  | Activity Resource Requirements | Networking |  | planning
|  |  |  | Enterprise Environmental Factors | Organization Theory |  | planning
|  |  |  | Organization Process assets | Expert Judgment |  | planning
[5 empty] | meeting |  | planning
| COMMUNICATION | 19 | Plan Communication management | Project Management Plan | Communication Requirements Analys | Communication Management Plan | planning
|  |  |  | Stakeholder Register | Communication Technology | Project Document Updates | planning
|  |  |  | Enterprise Environmental Factors | Communication Models |  | planning
|  |  |  | Organization Process assets | Communication Methods |  | planning
[5 empty] | meeting |  | planning
| RISK | 20 | Plan Risk Management | Project Management Plan | analytical techniques | Risk Management Plan | planning
|  |  |  | Project Charter | Expert Judgment |  | planning
|  |  |  | Stakeholder Register | meeting |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| RISK | 21 | Identify Risks | Risk Management Plan | Documentation Reviews | Risk Register | planning
|  |  |  | Cost Management Plan | Information- Gathering Techniques |  | planning
|  |  |  | Schedule Management Plan | Checklist Analysis |  | planning
|  |  |  | Quality Management Plan | Assumption Analysis |  | planning
|  |  |  | HR management plan | Diagramming Techniques |  | planning
|  |  |  | Scope Baseline | SWOT Analysis |  | planning
|  |  |  | Activity Cost Estimate | Expert Judgment |  | planning
|  |  |  | Activity Duration Estimate |  |  | planning
|  |  |  | Stakeholder Register |  |  | planning
|  |  |  | Project Documents |  |  | planning
|  |  |  | Procurement Documents |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| RISK | 22 | Perform Qualitative Risk Analysis | Risk Management Plan | Risk probability & impact assessment | Project Document Updates | planning
|  |  |  | Scope Baseline | Probability and Impact Matrix |  | planning
|  |  |  | Risk Register | Risk Data Quality Assessment |  | planning
|  |  |  | Enterprise Environmental Factors | Risk Categorization |  | planning
|  |  |  | Organization Process assets | Risk Urgency Assessment |  | planning
[5 empty] | Expert Judgment |  | planning
| RISK | 23 | Perform Quantitative Risk Analysis | Risk Management Plan | Data Gathering & Representation Techniques | Project Document Updates | planning
|  |  |  | Cost Management Plan | Quantitative Risk Analysis and Modeling techniques |  | planning
|  |  |  | Schedule Management Plan | Expert Judgment |  | planning
|  |  |  | Risk Register |  |  | planning
|  |  |  | Enterprise Environmental Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| RISK | 24 | Plan Risk Response | Risk Management Plan | Strategies For Negative Risk or Threats | Project Management Plan Update | planning
|  |  |  | Risk Register | Strategies For Positive Risk or Opportunities | Project Document Updates | planning
[5 empty] | Contingent Response Strategies |  | planning
[5 empty] | Expert Judgment |  | planning
| PROCUREMENTS | 25 | Plan Procurement management | project management plan | Make-or-Buy Analysis | Procurement Management Plan | planning
|  |  |  | Requirement Documentation | Expert Judgment | Procurement Statement Of Work | planning
|  |  |  | Risk Register | maket research | Procurement Documents | planning
|  |  |  | Activity Resource Requirements | meeting | Source Selection Criteria | planning
|  |  |  | Project Schedule |  | Make-Or-Buy Decision | planning
|  |  |  | Activity Cost Estimate |  | Change Request | planning
|  |  |  | Stakeholder Register |  | Project Document Updates | planning
|  |  |  | Environmental and organizational Factors |  |  | planning
|  |  |  | Organization Process assets |  |  | planning
| project STAKEHOLDER MANG. | 26 | plan stakeholder management | project management plan | Expert Judgment | stakeholder Management plan | planning
|  |  |  | Stakeholder Register | meeting | Project Document Updates | planning
|  |  |  | Enterprise Environmental Factors | analytical techniques |  | planning
|  |  |  | Organization Process assets |  |  | planning
EXECUTING | INTEGRATION | 27 | Direct and Manage Project work | Project Management Plan | Expert Judgment | Deliverables | EXECUTING
|  |  |  | Approved Change Request | Project Management Information System (PMIS) | Work Performance Information | EXECUTING
|  |  |  | Enterprise Environmental Factors | meeting | Change Request | EXECUTING
|  |  |  | Organization Process assets |  | Project Management Plan Update | EXECUTING
[6 empty] | Project Document Updates | EXECUTING
| QUALITY | 28 | Perform Quality Assurance | Quality Management Plan | Quality management and Perform control tools | Change Request | EXECUTING
|  |  |  | process improvement plan | Quality Audits | Project Management Plan Update | EXECUTING
|  |  |  | Quality Metrics | Process Analysis | Project Document Updates | EXECUTING
|  |  |  | Quality Control Measurements |  | Organization Process assets Updates | EXECUTING
|  |  |  | Project Documents |  |  | EXECUTING
| HUMAN RESOURCE | 29 | Acquire Project Team | HR management plan | Pre-assignment | Project Staff assignment | EXECUTING
|  |  |  | Enterprise Environmental Factors | Negotiation | Resource Calendars | EXECUTING
|  |  |  | Organization Process assets | Acquisition | Project Management Plan Update | EXECUTING
[5 empty] | Virtual Teams |  | EXECUTING
[5 empty] | Multi criteria decision analysis |  | EXECUTING
| HUMAN RESOURCE | 30 | Develop Project Team | HR management plan | Interpersonal Skills | Team Performance Assessment | EXECUTING
|  |  |  | Project Staff assignment | Training | Enterprise Environmental Factors Updates | EXECUTING
|  |  |  | Resource Calendars | Team-Building Activities |  | EXECUTING
[5 empty] | Ground Rules |  | EXECUTING
[5 empty] | Co-Location |  | EXECUTING
[5 empty] | Recognition and Reward |  | EXECUTING
[5 empty] | Personal assessment tools |  | EXECUTING
| HUMAN RESOURCE | 31 | Manage Project Team | HR management plan | Observation and Conversation | Change Request | EXECUTING
|  |  |  | Project Staff assignment | Project Performance Appraisals | Project Management Plan Update | EXECUTING
|  |  |  | Team Performance Assessment | Conflict Management | Project Document Updates | EXECUTING
|  |  |  | Issue Log | Interpersonal Skills | Enterprise Environmental Factors Updates | EXECUTING
|  |  |  | Work Performance report |  | Organization Process assets Update | EXECUTING
|  |  |  | Organization Process assets |  |  | EXECUTING
| COMMUNICATION | 32 | Manage communications | Communication Management Plan | Communication Methods | project communication | EXECUTING
|  |  |  | Work Performance report | Interpersonal Skills | Project Management Plan Update | EXECUTING
|  |  |  | Enterprise Environmental Factors | Management Skills | Project Document Updates | EXECUTING
|  |  |  | Organization Process assets |  | Organization Process assets Updates | EXECUTING
| PROCUREMENTS | 33 | Conduct Procurement | Procurement Management Plan | Bidder Conferences | Selected Sellers | EXECUTING
|  |  |  | Procurement Documents | Proposal Evaluation Techniques | agreements | EXECUTING
|  |  |  | Source Selection Criteria | Independent Estimates | Resource Calendars | EXECUTING
|  |  |  | Sellers Proposals | Expert Judgment | Change Request | EXECUTING
|  |  |  | Project Documents | Advertising | Project Management Plan Update | EXECUTING
|  |  |  | Make-Or-Buy Decision | analytical techniques | Project Document Updates | EXECUTING
|  |  |  | precurement statement of work | Procurement Negotiation |  | EXECUTING
|  |  |  | Organization Process assets |  |  | EXECUTING
| project STAKEHOLDER MANG. | 34 | Manage stakeholder engagement | stakeholder Management plan | Communication Methods | issue log | EXECUTING
|  |  |  | Communication Management Plan | Interpersonal Skills | Change Request | EXECUTING
|  |  |  | change log | Management Skills | Project Management Plan Update | EXECUTING
|  |  |  | Organization Process assets |  | Project Document Updates | EXECUTING
[6 empty] | Organization Process assets Updates | EXECUTING
MONITORING&CONTROLING | INTEGRATION | 35 | Monitor and Control Project Work | Project Management Plan | Expert Judgment | Change Request | monit&contr
|  |  |  | scheduale forecasts | analytical techniques | work performance reports | monit&contr
|  |  |  | cost forecasts | Project Management Information System (PMIS) | Project Management Plan Update | monit&contr
|  |  |  | Validated Changes | meeting | Project Document Updates | monit&contr
|  |  |  | Work Performance Information |  |  | monit&contr
|  |  |  | Enterprise Environmental Factors |  |  | monit&contr
|  |  |  | Organization Process assets |  |  | monit&contr
| INTEGRATION | 36 | Perform Integrated Change Control | Project Management Plan | Expert Judgment | approved change requests | monit&contr
|  |  |  | Work Performance report | meeting | change log | monit&contr
|  |  |  | Change Request | Change Control tools | Project Management Plan Update | monit&contr
|  |  |  | Enterprise Environmental Factors |  | Project Document Updates | monit&contr
|  |  |  | Organization Process assets |  |  | monit&contr
| SCOPE | 37 | validate Scope | Project Management Plan | Inspection | Accepted Deliverables | monit&contr
|  |  |  | Requirement Documentation |  | Change Request | monit&contr
|  |  |  | Requirement Traceability Matrix |  | Work Performance Information | monit&contr
|  |  |  | Validated Deliverables | Group Decision Making Techniques | Project Document Updates | monit&contr
|  |  |  | Work Performance data |  |  | monit&contr
| SCOPE | 38 | Control Scope | Project Management Plan | Variance Analysis | Work Performance Information | monit&contr
|  |  |  | Requirement Documentation |  | Change Request | monit&contr
|  |  |  | Requirement Traceability Matrix |  | Project Management Plan Update | monit&contr
|  |  |  | Work Performance data |  | Project Document Updates | monit&contr
|  |  |  | Organization Process assets |  | Organization Process assets Updates | monit&contr
| TIME | 39 | Control Schedule | Project Management Plan | Performance Review | Work Performance Information | monit&contr
|  |  |  | Project Schedule | Project Management Software | scheduale forecasts | monit&contr
|  |  |  | Work Performance data | Resource optimization techniques | Change Request | monit&contr
|  |  |  | Project Calendars | modeling techniques | Project Management Plan Update | monit&contr
|  |  |  | schedule data | leads and lag | Project Document Updates | monit&contr
|  |  |  | Organization Process assets | Schedule Compression | Organization Process assets Updates | monit&contr
[5 empty] | Scheduling Tool |  | monit&contr
| COST | 40 | Control Costs | Project Management Plan | Earned Value Management | Work Performance Measurement | monit&contr
|  |  |  | Project Funding Requirements | Forecasting | cost forecasts | monit&contr
|  |  |  | Work Performance Information | To-Complete Performance Index"TCPI" | Change Request | monit&contr
|  |  |  | Organization Process assets | Performance Review | Project Management Plan Update | monit&contr
[5 empty] | Project Management Software | Project Document Updates | monit&contr
[5 empty] | Reserve Analysis | Organization Process assets Updates | monit&contr
| QUALITY | 41 | Control Quality | Project Management Plan | Seven basic quality tools | Quality Control Measurements | monit&contr
|  |  |  | Quality Metrics | Statical Sampling | Validated Changes | monit&contr
|  |  |  | Quality Checklists | Inspection | Validated Deliverables | monit&contr
|  |  |  | Work Performance data | Approved Change Request Review | Work Performance Information | monit&contr
|  |  |  | Approved Change Request |  | Change Request | monit&contr
|  |  |  | Deliverables |  | Project Management Plan Update | monit&contr
|  |  |  | Project Documents |  | Project Document Updates | monit&contr
|  |  |  | Organization Process assets |  | Organization Process assets Update | monit&contr
| COMMUNICATION | 42 | control communications | Project Management Plan | information management system | Work Performance Information | monit&contr
|  |  |  | project communication | Expert Judgment | Change Request | monit&contr
|  |  |  | Issue Log | meeting | Project Management Plan Update | monit&contr
|  |  |  | Work Performance data |  | Project Document Updates | monit&contr
|  |  |  | Organization Process assets |  | Organization Process assets Update | monit&contr
| RISK | 43 | Control Risks | Project Management Plan | Risk Reassessment | Work Performance Information | monit&contr
|  |  |  | Risk Register | Risk Audits | Change Request | monit&contr
|  |  |  | Work Performance data | Variance and Trend Analysis | Project Management Plan Update | monit&contr
|  |  |  | Work Performance report | Technical Performance Measurement | Project Document Updates | monit&contr
[5 empty] | Reserve Analysis | Organization Process assets Update | monit&contr
[5 empty] | Meetings |  | monit&contr
| PROCUREMENTS | 44 | control Procurements | Project Management Plan | Contract Change Control System | Work Performance Information | monit&contr
|  |  |  | Procurement Documents | Procurement Performance Reviews | Change Request | monit&contr
|  |  |  | agreements | Inspections and Audits | Project Management Plan Update | monit&contr
|  |  |  | Approved Change Request | Performance Reporting | Project Document Updates | monit&contr
|  |  |  | Work Performance report | Payment Systems | Organization Process assets Updates | monit&contr
|  |  |  | Work Performance data | Claims administration |  | monit&contr
[5 empty] | Record Management System |  | monit&contr
| project STAKEHOLDER MANG. | 45 | control stakeholder engagement | Project Management Plan | information management system | Work Performance Information | monit&contr
|  |  |  | Issue Log | Expert Judgment | Change Request | monit&contr
|  |  |  | Work Performance data | meeting | Project Management Plan Update | monit&contr
|  |  |  | Procurement Documents |  | Project Document Updates | monit&contr
[6 empty] | Organization Process assets Updates | monit&contr
CLOSING | INTEGRATION | 46 | Close Project Or Phase | Project Management Plan | Expert Judgment | Final Product, Service or Result Transition | CLOSING
|  |  |  | Accepted Deliverables | analytical techniques | Organization Process assets Updates | CLOSING
|  |  |  | Organization Process assets | meeting |  | CLOSING
| PROCUREMENTS | 47 | Close Procurement | Project Management Plan | Procurement Audits | Closed Procurements | CLOSING
|  |  |  | Procurement Documents | Procurement Negotiation | Organization Process assets Updates | CLOSING
[5 empty] | Record Management System |  | CLOSING