## Sheet1
Process Group & Knowledg Area Maping ITTO ----- Created by: www.MonzerOsama.com
Project Process Groups | Knowledg Area | S.N | Process | INPUTS | Tools and Techniques | OUTPUTS
Initiating | Integration | 1 | Develop Project Charter | Project statement of work | Expert Judgment | Project Charter
Initiating | Integration |  |  | Business case
Initiating | Integration |  |  | Contract
Initiating | Integration |  |  | Enterprise Environmental Factors
Initiating | Integration |  |  | Organization Process assets
Initiating | Communication | 2 | Identify Stakeholders | Project Charter | Stakeholder Analysis | Stakeholder Register
Initiating | Communication |  |  | Procurement Documents
Initiating | Communication |  |  | Enterprise Environmental Factors | Expert Judgment | Stakeholder Management Strategy
Initiating | Communication |  |  | Organization Process assets
Planning | Integration | 3 | Develop Project Management Plan | Project Charter | Expert Judgment | Project Management Plan
Planning | Integration |  |  | Outputs From Planning Process
Planning | Integration |  |  | Enterprise Environmental Factors
Planning | Integration |  |  | Organization Process assets
Planning | Scope | 4 | Collect Requirements | Project Charter | Interviews | Requirement Documentation
Planning | Scope |  |  | Stakeholder Register | Focus Groups | Requirement Management Plan
Planning | Scope |  |  |  | Facilitated Workshops | Requirements Traceability Matrix
Planning | Scope |  |  |  | Group Creativity Techniques
Planning | Scope |  |  |  | Group Decision Making Techniques
Planning | Scope |  |  |  | Questionnaires and Surveys
Planning | Scope |  |  |  | Observations
Planning | Scope |  |  |  | Prototypes
Planning | Scope | 5 | Define Scope | Project Charter | Expert Judgment | Project Scope Statement
Planning | Scope |  |  | Requirement Documentation | Product analysis | Project Document Updates
Planning | Scope |  |  | Organization Process assets | Alternatives Identification
Planning | Scope |  |  |  | Facilitated Workshops
Planning | Scope | 6 | Create WBS | Project Scope Statement | Decomposition | WBS
Planning | Scope |  |  | Requirement Documentation |  | WBS Dictionary
Planning | Scope |  |  | Organization Process assets |  | Scope Baseline
Planning | Scope |  |  |  |  | Project Document Updates
Planning | Time | 7 | Define Activities | Scope Baseline | Decomposition | Activity List
Planning | Time |  |  | Enterprise Environmental Factors | Rolling Wave Planning | Activity Attributes
Planning | Time |  |  | Organization Process assets | Templates | Milestone List
Planning | Time |  |  |  | Expert Judgment
Planning | Time | 8 | Sequence Activities | Activity List | Precedence Diagramming Method (PDM) | Project Schedule Network Diagram
Planning | Time |  |  | Activity Attributes | Dependency Determination | Project Document Updates
Planning | Time |  |  | Milestone List | Applying Leads and Lags
Planning | Time |  |  | Project Scope Statement | Schedule Network Templates
Planning | Time |  |  | Organization Process assets
Planning | Time | 9 | Estimate Activity Resources | Activity List | Expert Judgment | Activity Resource Requirements
Planning | Time |  |  | Activity Attributes | Alternatives Analysis | Resource Breakdown Structure
Planning | Time |  |  | Resource Calendars | Published Estimating Data | Project Document Updates
Planning | Time |  |  | Enterprise Environmental Factors | Bottom-Up Estimating
Planning | Time |  |  | Organization Process assets | Project Management Software
Planning | Time | 10 | Estimate Activity Duration | Activity List | Expert Judgment | Activity Duration Estimate
Planning | Time |  |  | Activity Attributes | Analogous Estimating | Project Document Updates
Planning | Time |  |  | Activity Resource Requirements | Parametric Estimating
Planning | Time |  |  | Resource Calendars | Three-Point Estimates
Planning | Time |  |  | Project Scope Statement | Reserve Analysis
Planning | Time |  |  | Enterprise Environmental Factors
Planning | Time |  |  | Organization Process assets
Planning | Time | 11 | Develop Schedule | Activity List | Schedule Network Analysis | Project Schedule
Planning | Time |  |  | Activity Attributes | Critical Path Method | Schedule Baseline
Planning | Time |  |  | Project Schedule Network Diagram | Critical Chain Method | Schedule Data
Planning | Time |  |  | Activity Resource Requirements | Resource Leveling | Project Document Updates
Planning | Time |  |  | Resource Calendars | What-if Scenario Analysis
Planning | Time |  |  | Activity Duration Estimate | Applying Leads and Lags
Planning | Time |  |  | Project Scope Statement | Schedule Compression
Planning | Time |  |  | Enterprise Environmental Factors | Scheduling Tool
Planning | Time |  |  | Organization Process assets
Planning | Cost | 12 | Estimate Costs | Scope Baseline | Expert Judgment | Activity Cost Estimate
Planning | Cost |  |  | Project Schedule | Analogous Estimating | Basis Of Estimate
Planning | Cost |  |  | Human Resource Plan | Parametric Estimating | Project Document Updates
Planning | Cost |  |  | Risk Register | Bottom-Up Estimating
Planning | Cost |  |  | Enterprise Environmental Factors | Three-Point Estimates
Planning | Cost |  |  | Organization Process assets | Reserve Analysis
Planning | Cost |  |  |  | Cost of Quality
Planning | Cost |  |  |  | Project Management Estimating Software
Planning | Cost |  |  |  | Vendor Bid Analysis
Planning | Cost | 13 | Determine Budget | Activity Cost Estimate | Cost Aggregation | Cost Performance Baseline
Planning | Cost |  |  | Basis Of Estimate | Reserve Analysis | Project Funding Requirements
Planning | Cost |  |  | Scope Baseline | Expert Judgment | Project Document Updates
Planning | Cost |  |  | Project Schedule | Historical Relationships
Planning | Cost |  |  | Resource Calendars | Funding Limit Reconciliation
Planning | Cost |  |  | Contract
Planning | Cost |  |  | Organization Process assets
Planning | Quality | 14 | Plan Quality | Scope Baseline | Cost-Benefit Analysis | Quality Management Plan
Planning | Quality |  |  | Stakeholder Register | Cost of Quality | Quality Metrics
Planning | Quality |  |  | Cost Performance Baseline | Control Charts | Quality Checklists
Planning | Quality |  |  | Schedule Baseline | Benchmarking | Process Improvement Plan
Planning | Quality |  |  | Risk Register | Design of Experiments | Project Document Updates
Planning | Quality |  |  | Enterprise Environmental Factors | Statical Sampling
Planning | Quality |  |  | Organization Process assets | Flowcharting
Planning | Quality |  |  |  | Proprietary quality Management Methodology
Planning | Quality |  |  |  | Additional Quality Planning Tools
Planning | Human Resource | 15 | Develop Human Resource Plan | Activity Resource Requirements | Organization Chart and Position Description | Human Resource Plan
Planning | Human Resource |  |  | Enterprise Environmental Factors | Networking
Planning | Human Resource |  |  | Organization Process assets | Organization Theory
Planning | Communication | 16 | Plan Communications | Stakeholder Register | Communication Requirements Analysis | Communication Management Plan
Planning | Communication |  |  | Stakeholder Management Strategy | Communication Technology | Project Document Updates
Planning | Communication |  |  | Enterprise Environmental Factors | Communication Models
Planning | Communication |  |  | Organization Process assets | Communication Methods
Planning | Risk | 17 | Plan Risk Management | Project Scope Statement | Planning Meetings and Analysis | Risk Management Plan
Planning | Risk |  |  | Cost Management Plan
Planning | Risk |  |  | Schedule Management Plan
Planning | Risk |  |  | Communication Management Plan
Planning | Risk |  |  | Enterprise Environmental Factors
Planning | Risk |  |  | Organization Process assets
Planning | Risk | 18 | Identify Risks | Risk Management Plan | Documentation Reviews | Risk Register
Planning | Risk |  |  | Activity Cost Estimate | Information Gathering Techniques
Planning | Risk |  |  | Activity Duration Estimate | Checklist Analysis
Planning | Risk |  |  | Scope Baseline | Assumption Analysis
Planning | Risk |  |  | Stakeholder Register | Diagramming Techniques
Planning | Risk |  |  | Cost Management Plan | SWOT Analysis
Planning | Risk |  |  | Schedule Management Plan | Expert Judgment
Planning | Risk |  |  | Quality Management Plan
Planning | Risk |  |  | Project Documents
Planning | Risk |  |  | Enterprise Environmental Factors
Planning | Risk |  |  | Organization Process assets
Planning | Risk | 19 | Perform Qualitative Risk Analysis | Risk Register | Risk Probability and Impact Assessment | Risk Register Update
Planning | Risk |  |  | Risk Management Plan | Probability and Impact Matrix
Planning | Risk |  |  | Project Scope Statement | Risk Data Quality Assessment
Planning | Risk |  |  | Organization Process assets | Risk Categorization
Planning | Risk |  |  |  | Risk Urgency Assessment
Planning | Risk |  |  |  | Expert Judgment
Planning | Risk | 20 | Perform Quantitative Risk Analysis | Risk Register | Data Gathering and Representation Techniques | Risk Register Update
Planning | Risk |  |  | Risk Management Plan | Quantitative Risk Analysis and Modeling Techniques
Planning | Risk |  |  | Cost Management Plan | Expert Judgment
Planning | Risk |  |  | Schedule Management Plan
Planning | Risk |  |  | Organization Process assets
Planning | Risk | 21 | Plan Risk Response | Risk Register | Strategies For Negative Risk or Threats | Risk Register Update
Planning | Risk |  |  | Risk Management Plan | Strategies For Positive Risk or Opportunities | Risk-Related Contract Decision
Planning | Risk |  |  |  | Contingent Response Strategies | Project Management Plan Update
Planning | Risk |  |  |  | Expert Judgment | Project Document Updates
Planning | Procurements | 22 | Plan Procurements | Scope Baseline | Make-or-Buy Analysis | Procurement Management Plan
Planning | Procurements |  |  | Requirement Documentation | Expert Judgment | Procurement Statement Of Work
Planning | Procurements |  |  | Teaming Agreements | Contract Types | Make-Or-Buy Decision
Planning | Procurements |  |  | Risk Register |  | Procurement Documents
Planning | Procurements |  |  | Risk-Related Contract Decision |  | Source Selection Criteria
Planning | Procurements |  |  | Activity Resource Requirements |  | Change Request
Planning | Procurements |  |  | Project Schedule
Planning | Procurements |  |  | Activity Cost Estimate
Planning | Procurements |  |  | Cost Performance Baseline
Planning | Procurements |  |  | Enterprise Environmental Factors
Planning | Procurements |  |  | Organization Process assets
Executing | Integration | 23 | Direct and Manage Project Execution | Project Management Plan | Expert Judgment | Deliverables
Executing | Integration |  |  | Approved Change Request | Project Management Information System | Work Performance Information
Executing | Integration |  |  | Enterprise Environmental Factors |  | Change Request
Executing | Integration |  |  | Organization Process assets |  | Project Management Plan Update
Executing | Integration |  |  |  |  | Project Document Updates
Executing | Quality | 24 | Perform Quality Assurance | Project Management Plan | Plan Quality and Perform Quality Control Tools and Techniques | Organization Process assets Update
Executing | Quality |  |  | Quality Metrics |  | Change Request
Executing | Quality |  |  | Work Performance Information | Quality Audits | Project Management Plan Update
Executing | Quality |  |  | Quality Control Measurements | Process Analysis | Project Document Updates
Executing | Human Resource | 25 | Acquire Project Team | Project Management Plan | Pre-assignment | Project Staff assignment
Executing | Human Resource |  |  | Enterprise Environmental Factors | Negotiation | Resource Calendars
Executing | Human Resource |  |  | Organization Process assets | Acquisition | Project Management Plan Update
Executing | Human Resource |  |  |  | Virtual Teams
Executing | Human Resource | 26 | Develop Project Team | Project Staff assignment | Interpersonal Skills | Team Performance Assessment
Executing | Human Resource |  |  | Project Management Plan | Training | Enterprise Environmental Factors Updates
Executing | Human Resource |  |  | Resource Calendars | Team-Building Activities
Executing | Human Resource |  |  |  | Ground Rules
Executing | Human Resource |  |  |  | Co-Location
Executing | Human Resource |  |  |  | Recognition and Reward
Executing | Human Resource | 27 | Manage Project Team | Project Staff assignment | Observation and Conversation | Enterprise Environmental Factors Updates
Executing | Human Resource |  |  | Project Management Plan | Project Performance Appraisals | Organization Process assets Update
Executing | Human Resource |  |  | Team Performance Assessment | Conflict Management | Change Request
Executing | Human Resource |  |  | Performance Reports | Issue Log | Project Management Plan Update
Executing | Human Resource |  |  | Organization Process assets | Interpersonal Skills
Executing | Communication | 28 | Distribute Information | Project Management Plan | Communication Methods | Organization Process assets Update
Executing | Communication |  |  | Performance Reports | Information Distribution Tools
Executing | Communication |  |  | Organization Process assets
Executing | Communication | 29 | Manage Stakeholders Expectation | Stakeholder Register | Communication Methods | Organization Process assets Update
Executing | Communication |  |  | Stakeholders Management strategy | Interpersonal Skills | Change Request
Executing | Communication |  |  | Project Management Plan | Management Skills | Project Management Plan Update
Executing | Communication |  |  | Issue Log |  | Project Document Updates
Executing | Communication |  |  | Change Log
Executing | Communication |  |  | Organization Process assets
Executing | Procurements | 30 | Conduct Procurement | Project Management Plan | Bidder Conferences | Selected Sellers
Executing | Procurements |  |  | Procurement Documents | Proposal Evaluation Techniques | Procurement Contract Award
Executing | Procurements |  |  | Source Selection Criteria | Independent Estimates | Resource Calendars
Executing | Procurements |  |  | Qualified Seller List | Expert Judgment | Change Request
Executing | Procurements |  |  | Sellers Proposals | Advertising | Project Management Plan Update
Executing | Procurements |  |  | Project Documents | Internet search | Project Document Updates
Executing | Procurements |  |  | Make-Or-Buy Decision | Procurement Negotiation
Executing | Procurements |  |  | Teaming Agreements
Executing | Procurements |  |  | Organization Process assets
Monitoring & Controling | Integration | 31 | Monitor and Control Project Work | Project Management Plan | Expert Judgment | Change Request
Monitoring & Controling | Integration |  |  | Performance Reports | Project Management Information System | Project Management Plan Update
Monitoring & Controling | Integration |  |  | Enterprise Environmental Factors |  | Project Document Updates
Monitoring & Controling | Integration |  |  | Organization Process assets
Monitoring & Controling | Integration | 32 | Perform Integrated Change Control | Project Management Plan | Expert Judgment | Change Request Status Update
Monitoring & Controling | Integration |  |  | Work Performance Information | Change Control Meeting | Project Management Plan Update
Monitoring & Controling | Integration |  |  | Change Request |  | Project Document Updates
Monitoring & Controling | Integration |  |  | Enterprise Environmental Factors
Monitoring & Controling | Integration |  |  | Organization Process assets
Monitoring & Controling | Scope | 33 | Verify Scope | Project Management Plan | Inspection | Accepted Deliverables
Monitoring & Controling | Scope |  |  | Requirement Documentation |  | Change Request
Monitoring & Controling | Scope |  |  | Requirement Traceability Matrix |  | Project Document Updates
Monitoring & Controling | Scope |  |  | Validated Deliverables
Monitoring & Controling | Scope | 34 | Control Scope | Project Management Plan | Variance Analysis | Work Performance Measurement
Monitoring & Controling | Scope |  |  | Work Performance Information |  | Organization Process assets Update
Monitoring & Controling | Scope |  |  | Requirement Documentation |  | Change Request
Monitoring & Controling | Scope |  |  | Requirement Traceability Matrix |  | Project Management Plan Update
Monitoring & Controling | Scope |  |  | Organization Process assets |  | Project Document Updates
Monitoring & Controling | Time | 35 | Control Schedule | Project Management Plan | Performance Review | Work Performance Measurement
Monitoring & Controling | Time |  |  | Project Schedule | Variance Analysis | Organization Process assets Update
Monitoring & Controling | Time |  |  | Work Performance Information | Project Management Software | Change Request
Monitoring & Controling | Time |  |  | Organization Process assets | Resource Leveling | Project Management Plan Update
Monitoring & Controling | Time |  |  |  | What-if Scenario Analysis | Project Document Updates
Monitoring & Controling | Time |  |  |  | Adjusting Leads and Lags
Monitoring & Controling | Time |  |  |  | Schedule Compression
Monitoring & Controling | Time |  |  |  | Scheduling Tool
Monitoring & Controling | Cost | 36 | Control Cost | Project Management Plan | Earned Value Management | Work Performance Measurement
Monitoring & Controling | Cost |  |  | Project Funding Requirements | Forecasting | Budget Forecast
Monitoring & Controling | Cost |  |  | Work Performance Information | To-Complete Performance Index | Organization Process assets Update
Monitoring & Controling | Cost |  |  | Organization Process assets | Performance Review | Change Request
Monitoring & Controling | Cost |  |  |  | Variance Analysis | Project Management Plan Update
Monitoring & Controling | Cost |  |  |  | Project Management Software | Project Document Updates
Monitoring & Controling | Quality | 37 | Perform Quality Control | Project Management Plan | Cause and Effect Diagram | Quality Control Measurements
Monitoring & Controling | Quality |  |  | Quality Metrics | Control Charts | Validated Changes
Monitoring & Controling | Quality |  |  | Quality Checklists | Flowcharting | Validated Deliverables
Monitoring & Controling | Quality |  |  | Work Performance Measurement | Histograms | Organization Process assets Update
Monitoring & Controling | Quality |  |  | Approved Change Request | Pareto Charts | Change Request
Monitoring & Controling | Quality |  |  | Deliverables | Run chart | Project Management Plan Update
Monitoring & Controling | Quality |  |  | Organization Process assets | Scatter Diagram | Project Document Updates
Monitoring & Controling | Quality |  |  |  | Statical Sampling
Monitoring & Controling | Quality |  |  |  | Inspection
Monitoring & Controling | Quality |  |  |  | Approved Change Request Review
Monitoring & Controling | Communication | 38 | Report Performance | Project Management Plan | Variance Analysis | Performance Reports
Monitoring & Controling | Communication |  |  | Work Performance Information | Forecasting Methods | Organization Process assets Update
Monitoring & Controling | Communication |  |  | Work Performance Measurement | Communication Methods | Change Request
Monitoring & Controling | Communication |  |  | Budget Forecast | Reporting System
Monitoring & Controling | Communication |  |  | Organization Process assets
Monitoring & Controling | Risk | 39 | Monitor and Control Risks | Risk Register | Risk Reassessment | Risk Register Update
Monitoring & Controling | Risk |  |  | Project Management Plan | Risk Audits | Organization Process assets Update
Monitoring & Controling | Risk |  |  | Work Performance Information | Variance and Trend Analysis | Change Request
Monitoring & Controling | Risk |  |  | Performance Reports | Technical Performance Measurement | Project Management Plan Update
Monitoring & Controling | Risk |  |  |  | Reserve Analysis | Project Document Updates
Monitoring & Controling | Risk |  |  |  | Status Meetings
Monitoring & Controling | Procurements | 40 | Administer Procurements | Procurement Documents | Contract Change Control System | Procurement Documentation
Monitoring & Controling | Procurements |  |  | Project Management Plan | Procurement Performance Reviews | Organization Process assets Update
Monitoring & Controling | Procurements |  |  | Contract | Inspections and Audits | Change Request
Monitoring & Controling | Procurements |  |  | Performance Reports | Performance Reporting | Project Management Plan Update
Monitoring & Controling | Procurements |  |  | Approved Change Request | Payment Systems
Monitoring & Controling | Procurements |  |  | Work Performance Information | Claims administration
Monitoring & Controling | Procurements |  |  |  | Record Management System
Closing | Integration | 41 | Close Project Or Phase | Project Management Plan | Expert Judgment | Final Product, Service or Result Transition
Closing | Integration |  |  | Accepted Deliverables |  | Organization Process assets Update
Closing | Integration |  |  | Organization Process assets
Closing | Procurements | 42 | Close Procurement | Project Management Plan | Procurement Audits | Closed Procurements
Closing | Procurements |  |  | Procurement Documents | Negotiation Settlement | Organization Process assets Update
Closing | Procurements |  |  |  | Record Management System